## Introduction
Project Name
What is this? | This workbook is meant to help manage and piroritize the user stories and features using scrum.
How to use and read this document? | Before project start: The product owner is responsible for managing and maintaining the product backlog of user stories.
Before each sprint: The vendor will break down the user stories into tasks.
Notes | Cells that you can edit have a blue background.
Sprints are assumed to be 2 weeks long (10 working days)/
Licence | This work is licensed under a Creative Commons Attribution-Share Alike 3.0 Unported License.
Origins | This work is inspired by the Scrum Template published by Nicolas Martignole on his "Touilleur Express" blog. Adapted by Olivier Gérardin.

## Product backlog
Project Name
| Organizations | Pizzeria
| Project | Pizzeria Website
| Product Owner | Fasano, Cole
| Scrum Master | Landavazo, Gavin
| Development Team | Jance, Elion Landavazo, Gavin Fasano,Cole
Story ID | Title | Description | Acceptance Criteria | Priority # | Sprint # | Responsibility
E01 | User Friendly UI | The UI should be easy to navigate & use | The UI feels responsive & easy to navigate because time was spent ensuring ease of use. | 1 | 1 | Gavin
E02 | Menu Photos | Menu items should have photos attached to present them. | Each menu item, promotion, or discount has an appropriate photo to present them. | 2 | 1 | Elion
E03 | Promotions & Discounts | The menu will display current promotions & discounts | Current promotions & discounts are visible because promotions have been updated. | 3 | 1 | Gavin,Elion
E04 | Payment System | The system will handle payment & calculations | Each order calculates total payment when checking out. | 4 | 2 | Cole
E05 | Log in system | There will be admin & customer accounts. Admin account will be able to edit menu. | Admin accounts can edit menu items, customer accounts can make orders. | 5 | 2 | Gavin, Cole

## Sprint 1
Sprint #1Tracking Sheet
|  | Project |  | Pizzeria Website
|  | Sprint # |  | 1
|  | Start date |  | 2023-01-01
|  |  | Total Team Members | 3
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2023-01-01 | 2023-01-02 | 2023-01-03 | 2023-01-04 | 2023-01-05 | 2023-01-06 | 2023-01-07 | 2023-01-08 | 2023-01-09 | 2023-01-10 | 2023-01-11 | 2023-01-12 | 2023-01-13 | 2023-01-14
T01 | E01 | User Friendly UI, easy to navigate & use. | Gavin | 12:00
T02 | E02 | Photos for all menu items & promotions | Elion | 12:00
T03 | E03 | Update promotions & Discounts | Gavin, Elion | 12:00
|  | Remaining units (actual) |  | 48 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | 44.5714 | 41.1429 | 37.7143 | 34.2857 | 30.8571 | 27.4286 | 24 | 20.5714 | 17.1429 | 13.7143 | 10.2857 | 6.8571 | 3.4286 | 0
[10 empty] | 0 | 1.5 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0

## Sprint 2
Sprint #2Tracking Sheet
|  | Project |  | Pizzeria Website
|  | Sprint # |  | 2
|  | Start date |  | 2023-02-19
|  |  | Total Team Members | 3
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2023-02-19 | 2023-02-20 | 2023-02-21 | 2023-02-22 | 2023-02-23 | 2023-02-24 | 2023-02-25 | 2023-02-26 | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-03 | 2023-03-04
T04 | E04 | Total order calculations & payment | Cole | 16:00
T05 | E05 | Admin accounts to edit menu. | Gavin, Cole | 16:00
T06 | E05 | Implement account creation | Gavin, Cole | 12:00
T07 | E05 | Add manager menu modification capability | Gavin, Cole, Elion | 24:00
|  | Remaining units (actual) |  | 48 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | 44.5714 | 41.1429 | 37.7143 | 34.2857 | 30.8571 | 27.4286 | 24 | 20.5714 | 17.1429 | 13.7143 | 10.2857 | 6.8571 | 3.4286 | 0
[10 empty] | 0 | 2.8333 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0